## Sheet1
Schedule
| Gathering Requirement |  | Development |  | UAT & User Training
| 13 April – 25 June |  | 05 July – 10 December |  | 11 December – 24 December
Gathering Requerments
No. | Resource | Man | Day | Effort | ManDay IDR |  |  | Job | Fee | Margin (10%) | Fee + Margin
1 | Project Manager | 1 | 15 | 100% | 9900000 |  |  | Project Manager | 600000 | 60000 | 660000
2 | Analyst | 1 | 15 | 100% | 8250000 |  |  | Analyst | 500000 | 50000 | 550000
3 | Frontend | 1 | 15 | 100% | 5775000 |  |  | Fronted | 350000 | 35000 | 385000
4 | Web Developer | 1 | 15 | 100% | 4950000 |  |  | Web Developer | 300000 | 30000 | 330000
|  |  |  | Total | 28875000 |  |  | Quality Control | 250000 | 25000 | 275000
Development
No. | Resource | Man | Day | Effort | MAnDayIDR
1 | Project Manager | 1 | 85 | 100% | 56100000
2 | Analyst | 1 | 85 | 100% | 46750000
3 | Graphic Designer & Cut and Slice | 1 | 85 | 100% | 32725000
4 | Quality Control | 1 | 85 | 100% | 28050000
5 | Web Developer 1 | 1 | 85 | 100% | 23375000
6 | Web Developer 2 | 1 | 85 | 100% | 0
7 | Web Developer 3 | 1 | 85 | 100% | 0
|  |  |  | Total | 187000000
Deployment - UAT & Training
No. | Resource | Man | Day | Effort | MAnDayIDR
1 | Project Manager | 1 | 10 | 100% | 6600000
2 | Analyst | 1 | 2 | 100% | 1100000
3 | Quality Control | 1 | 4 | 100% | 1540000
4 | Web Developer 1 | 1 | 8 | 100% | 2640000
5 | Web Developer 2 | 1 | 6 | 100%
6 | Web Developer 3 | 1 | 6 | 100%
|  |  |  | Total | 11880000
Software Implementatin Costs |  |  |  | Total | 227755000
Overhead - Gathering 1st Week
Man | Day | Plane | PP BAT - Hotel | Hotel Room | Hotel | Allowance | Total
4 | 6 | 3500000 | 100000 | 2 | 600000 | 1500000 | 12300000
Overhead - Gathering 2nd Week
Man | Day | Plane | PP BAT - Hotel | Hotel Room | Hotel | Allowance | Total
4 | 6 | 3500000 | 100000 | 2 | 600000 | 1500000 | 12300000
Overhead - UAT 1st Week
Man | Day | Plane | PP BAT - Hotel | Hotel Room | Hotel | Allowance | Total
4 | 6 | 3500000 | 100000 | 2 | 600000 | 1500000 | 12300000
Overhead - UAT 2nd Week
Man | Day | Plane | PP BAT - Hotel | Hotel Room | Hotel | Allowance | Total
4 | 6 | 3500000 | 100000 | 2 | 600000 | 1500000 | 12300000
Overhead Cost |  | Total | 49200000
No. | Total Costs | 0 | 0 | 0
I | Software Implementation costs | 0 | 0 | 0
II | Overhead Costs | 0 | 0 | 0
III | Post Go Live Support (1 Month) | 0 | 0 | 0
| Total | 0 | 0 | 0
| Grand Total | 0 | 0 | 0
Apendix III – Maintenance Fee Yearly ( Optional )
Yearly Maintenance Support
Percentage | Total | Mandays
8% | 0 | 65
Apendix IV – Dedicated Team Help Desk ( Optional )
Dedicated Maintenance Support
Man | Effort | Rate Mandays | Work Days In A Years | Total
1 | 20% | 65 | 0 | 0